## Slide 1: Conquer Your ILS Upgrade
Mieko Fujiura-Landers
Member Services Librarian for Public Services, CCS
mlanders@ccslib.org

## Slide 2: Agenda
Background
Our Upgrade Toolkit
Our Upgrade Process
Questions

## Slide 3: Agenda
Scale
Up!
Scale Down!
= If you have the capacity for a little more
= If you have the capacity for a little less

## Slide 4
Background

## Slide 5: About Cooperative Computer Services
Catalog consortium in Chicago suburbs

## Slide 6: About Cooperative Computer Services
Catalog consortium in Chicago suburbs
30 libraries

## Slide 7: About Cooperative Computer Services
Catalog consortium in Chicago suburbs
30 libraries
9 staff

## Slide 8: About Cooperative Computer Services
Catalog consortium in Chicago suburbs
30 libraries
9 staff
Hosted Polaris site

## Slide 9: CCS and Upgrades
From December 2018 and August 2022, CCS led seven upgrades
April 2018
Live on 6.0
Dec 2018
6.1
Aug 2019
6.3
Aug 2020
6.5
June 2021
6.7
Dec 2021
7.0
May 2022
7.1
7.2
Aug 2022

## Slide 10
Our Upgrade Toolkit

## Slide 11: Our Upgrade Toolkit
  At first, didn't have documented procedure in place for upgrades
  Live and learn and then create documentation!
  Developed upgrade toolkit

## Slide 12: Our Upgrade Toolkit
  Innovative's "What's New" document
  Upgrade guide
  Communication scripts
  QA tasks

## Slide 13: Our Upgrade Toolkit
  Innovative's "What's New" document
  Upgrade guide
  Communication scripts
  QA tasks

## Slide 14: Our Upgrade Toolkit
  Innovative's "What's New" document
  Upgrade guide (LINK)
  Communication scripts
  QA tasks

## Slide 15: Our Upgrade Toolkit
The Upgrade Guide includes:
  What to do and when!
  Day-of upgrade notes
  Solutions for common post-upgrade issues
  Instructions for restoring PowerPAC customizations

## Slide 16
CCS Upgrade Guide

## Slide 17: Our Upgrade Toolkit
Tips for your Upgrade Guide
Keep track of potential issues you run into during testing and QA so you can check on them after production upgrade
Maintain running list of common issues and solutions that you can easily reference during each upgrade
Include important 3rd party vendor info

## Slide 18: Our Upgrade Toolkit
  Innovative's "What's New" document
  Upgrade guide
  Communication scripts (LINK)
  QA tasks

## Slide 19: Our Upgrade Toolkit
Communication Scripts include:
Messaging for newsletter alerts, emails to staff about training database upgrade
Messaging for newsletter alerts, email to staff about production database upgrade
Messaging for emails to IT staff about installing new version of local offline client

## Slide 20
CCS Communication Scripts

## Slide 21: Our Upgrade Toolkit
  Innovative's "What's New" document
  Upgrade guide
  Communication scripts
  QA tasks (LINK)

## Slide 22: Our Upgrade Toolkit
The QA Tasks spreadsheet includes
Tasks to test on the upgraded training database
Who is responsible for completing each task
Space for notes in case testers run into errors or issues

## Slide 23
CCS QA Task List

## Slide 24: Our Upgrade Toolkit
  Innovative's "What's New" document
  Upgrade guide
  Communication scripts
  QA tasks

## Slide 25: Our Upgrade Toolkit
Scale Up!
Page on website/intranet
Upgrade-related info in one spot
Dates for upgrade, downtime info
Training and documentation resources
Issues log

## Slide 26
Our Upgrade Process

## Slide 27: The Upgrade Process
  Decide if you want to upgrade
  Get organized
  Upgrade the training database
  Testing and QA
  Documentation and training staff
  Schedule production upgrade
  Upgrade

## Slide 28: The Upgrade Process
  Decide if you want to upgrade
  Get organized
  Upgrade the training database
  Testing and QA
  Documentation and training staff
  Schedule production upgrade
  Upgrade

## Slide 29: Step 1: Decide if You Want to Upgrade
Just because a software upgrade comes out does not mean you should automatically take it!

## Slide 30: Step 1: Decide if You Want to Upgrade
What to do
Review What’s New document for new features, Known Issues page for bug fixes
Watch webinars put on by iii to see an overview of new features
Considerations
Will you benefit from new features or Bug fixes?
Does it fit in with your current project schedule?

## Slide 31: The Upgrade Process
  Decide if you want to upgrade
  Get organized
  Upgrade the training database
  Testing and QA
  Documentation and training staff
  Schedule production upgrade
  Upgrade

## Slide 32: Step 2: Get Organized
Use your guides and scripts
Verify project steps in the Upgrade Guide
Verify communication strategy and scripts
Once you have an upgrade guide, this part won't take long!
Update QA Tasks
Add new features you want to test
Update QA assignments

## Slide 33: Step 2: Get Organized
  Figure out your priorities (examples: bug fixes, certain new Leap functions)
  Use that to inform the QA tasks and future steps, like training
Scale Down!

## Slide 34: The Upgrade Process
  Decide if you want to upgrade
  Get organized
  Upgrade the training database
  Testing and QA
  Documentation and training staff
  Schedule production upgrade
  Upgrade

## Slide 35: Step 3: Upgrade the Training Database
Coordinate training database upgrade with Innovative
Will you ask for a data sync between production and training?
Send communication as needed to your libraries or staff
Alerts that training will be upgraded and (if needed) data synced
Confirmation when training upgrade complete and available

## Slide 36: Step 3: Upgrade the Training Database
  Staff don't use the training database?
  Scale back on communication
Scale Down!

## Slide 37: The Upgrade Process
  Decide if you want to upgrade
  Get organized
  Upgrade the training database
  Testing and QA
  Documentation and training staff
  Schedule production upgrade
  Upgrade

## Slide 38: Step 4: Testing and QA
Once the training database is upgraded, you can start testing out new features and work through QA tasks.
QA tasks include:
  Standard actions we test every time
  New functions or features we would like to use
  Testing bug fixes
Solicit help from team or other library staff

## Slide 39: Step 4: Testing and QA
  Reduce QA tasks to features/actions your staff use or day-to-day essential functions
Scale Down!

## Slide 40: Step 4: Testing and QA
Issues come up during QA testing?
Decide if you need to postpone the upgrade.

## Slide 41: The Upgrade Process
  Decide if you want to upgrade
  Get organized
  Upgrade the training database
  Testing and QA
  Documentation and training staff
  Schedule production upgrade
  Upgrade

## Slide 42: Step 5: Documentation and Training Staff
  What needs staff training?
  New documentation?
  Updated documentation?
  What impacts current workflow?
  Do you need to update any SA settings?
Take a closer look at changes using the "What's New" document

## Slide 43: Step 5: Documentation and Training Staff
Inform staff of new features and/or bug fixes
Create in-house documentation or update procedure manuals as needed
Train staff on new features, workflow changes as needed

## Slide 44: Step 5: Documentation and Training Staff
  Get formal input on new functions or features that will change existing workflow
Scale Up!
Scale Down!
  Share "What's New" document with staff in place of training or in-house documentation

## Slide 45: The Upgrade Process
  Decide if you want to upgrade
  Get organized
  Upgrade the training database
  Testing and QA
  Documentation and training staff
  Schedule production upgrade
  Upgrade

## Slide 46: Step 6: Schedule Production Upgrade
Coordinate upgrade date and time with Site Manager
Confirm if you will do a data sync at the same time
Tip: Avoid upgrading at the end of the week. If you can, schedule upgrades for Monday or Tuesday. More staff will be on-hand to troubleshoot in the following days vs the weekend.

## Slide 47: Step 6: Schedule Production Upgrade
Inform staff of production upgrade
Use your communication scripts
We give libraries 3-4 week notice before production upgrade, with reminders 1 week and day-of the upgrade
Inform patrons of upgrade/catalog maintenance
Add an alert to library website
Alert banner on PowerPAC (LINK)
3rd party mobile apps may have an alert option, too!

## Slide 48: PAC Alert Banner
<div>
<p style="color:white; background-color: #e83e09; text-align: center; padding: 10px; margin: 0; font-size: 1.25em;">
Alert: On Tuesday, August 16th from 9:30 pm - 12:00 am, account access and catalog search will be unavailable due to a catalog upgrade. </p>
</div>

## Slide 49: Step 6: Schedule Production Upgrade
Prepare for upgrade
Know what needs to be done and who will do it
Includes post-upgrade QA, restoring any PAC customizations, sending communication to library staff
If you have an upgrade guide, you don't need to think about this!

## Slide 50: The Upgrade Process
  Decide if you want to upgrade
  Get organized
  Upgrade the training database
  Testing and QA
  Documentation and training staff
  Schedule production upgrade
  Upgrade

## Slide 51: Step 7: Upgrade
Innovative upgrades your production environment
After the upgrade is complete
  Do your post-upgrade QA
  Take care of any "Day-of Upgrade" notes
  Let staff know the database is available
  Finish any PAC adjustments/restore customizations
  Re-install local offline client and update MDB files
  Check on any “fixed in future release” tickets

## Slide 52: Step 7: Upgrade
Congratulate yourself on a job well done!

## Slide 53: Links to Toolkit Resources
CCS Upgrade Guide
CCS Communication Scripts
CCS QA Task Spreadsheet
PAC Alert Banner How-To

## Slide 54
THANK YOU
Questions?
Reach out to me at mlanders@ccslib.org!